## OPEN
ID | Title | Status | Effort | Importance | Description | Source | Notes
5 | v0.6 source-grounded rebuild of all 4 accreditor columns | Open. Multi-hour subagent fan-out work. Work-pass 2026-10-04: BLOCKED on materials. AABB and COLA columns cannot be source-grounded without the gated manuals (item #28); CAP is 11/12 modules verifi... | L (3-5 weeks) | High — accreditor citation accuracy underpins every VeritaPolicy / VeritaScan... | AABB ids in aabbRequirements.ts (138/168 marked "real") and COLA ids in colaRequirements.ts (167/168 marked "real") came from agent generator output, not from a human cross-check against the authoritative source documents (BBTS PDF for AABB, current COLA checklist PDF for COLA). Same concern less acute for CAP (12 MAS xlsx) and TJC (CAMLAB PDF + text extract). | prior session handoff. Re-confirmed during 2026-05-01 QC review. | Pre-COLA. May 6-8 conference; Saturday + Sunday + Monday available before the booth. --- _(item #17 reclassified to CLOSED 2026-09-28; VeritaResponse shipped and live, see C48 below)_ --- _(item #18 closed 2026-09-28; all phases shipped, see C47 below)_ --- _(item #22 closed 2026-05-28; see C26 below)_
27 | Acquire CAP MOL (Molecular) checklist to verify 2 pending entries | Open, blocks on operator obtaining the MOL checklist. Work-pass 2026-10-04: NEEDS MICHAEL. The MAS_MOL xlsx download requires CAP e-LAB credentials (agent cannot download). Drop MAS_MOL_*.xlsx in t... | N/A (operator action — ~1 hour of code work once the file is in hand) | Low — two entries total; low traffic; only matters when a customer cites a MO... | PR #108 left 2 entries in server/capRequirements.ts flagged as unverified because the operator does not hold the CAP MOL (Molecular Pathology) MAS xlsx file: - MOL.35855 - NGS HLA Discrepancy Resolution - MOL.37460 - Contamination Control The other 11 CAP modules (ANP, CHM, COM, CYP, DRA, GEN, HEM, IMM, MIC, POC, TRM, URN) were verified against the 12 MAS files held on the operator's local drive at C:/Users/veril/OneDrive - veritaslabservices com/Lab/Regulatory/2026 Cap checklists/. The MOL module's MAS xlsx is the only one missing from that set. | PR #108 commit 92f9573 (closed via merge 2026-05-11), audit findings. | Post-COLA. Two entries; low traffic.
28 | Acquire AABB Standards 35th edition + current COLA Accreditation Manual for exhaustive citation verification | Open, blocks on operator obtaining the gated accreditor manuals. Until then, AABB / COLA citations are best-effort against the public-source compilations. Work-pass 2026-10-04: NEEDS MICHAEL. AABB... | N/A (operator action — ~1-2 days of audit re-run once the manuals are held) | High — gates #5 from reaching "exhaustively verified" status for AABB and COLA. | The 2026-05-11 QC audit found that VeritaScan, cfrRequirements cross-refs, and colaRequirements.ts cite about 180 AABB and COLA codes that the public compilations (build_aabb_pdf.py / build_cola_pdf.py) do not cover. These are format-valid (correct chapter prefix and section format) and the master citation index treats many of them as real, but they cannot be exhaustively verified against authoritative source until the gated accreditor manuals are held. Examples (representative; not exhaustive): - AABB: 1.2.3, 1.2.4, 1.3.3, 2.1.6-2.3.2, 3.1.1+ - sequential AABB Standards for Blood Banks and Transfusion Services 35th edition (effective April 1, 2026) chapter codes. - COLA: APM 2-APM 16, CA 3-CA 6, FAC 11-FAC 14, MA 4, PST 23, VER 9 - real COLA criterion codes that the public 2013 manual + LabGuides + 2019 Validation excerpts compilation does not enumerate fully. | 2026-05-11 QC/QA audit, documented in OneDrive\Lab\Regulatory\aaa Truth Master Document\PROVENANCE.md "Audit-coverage limits" section. | Post-COLA. Operator-side action item, no code work pending until the source documents land.
29 | VeritaStock barcode scanning (full mobile scan flow) | Parked pending first paid commitment. Work-pass 2026-10-04: HELD BY STRATEGY, build-decision needs Michael. Already fully scoped (12-day plan below), so nothing to add by re-scoping. Trigger remain... | L (12 working days, ~3 weeks calendar) | High — strategic moat vs Unity Lab Services ($30K+/yr); presold as included o... | The remaining barcode-scanning build for VeritaStock, scoped during the 2026-05-20 Pfizer follow-up discussion. Order-now reorder document (PDF + Excel) already shipped in PR #286. This item is the mobile scan companion that turns VeritaStock into a true Unity Lab Services-class inventory product. | 2026-05-20 Pfizer follow-up session, after the order-now reorder document shipped (PR #286). Strategic decision documented in the team pricing analysis docx at C:\Users\veril\Downloads\VeritaAssure-Pricing-Analysis-2026-05-21.docx (version 2). The Request-an-Instrument feature (PR #293) was built instead as the durable customer-feedback channel for VeritaMap; barcode scanning waits on revenue...
32 | Lab leader community / forum (paid subscription idea) | Open. Work-pass 2026-10-04: BUSINESS DECISION, needs Michael. SWOT verdict stands (do not build a paid forum; economics kill it). The recommended free invite-only Slack/Discord plus quarterly round... | XL (ongoing operational commitment, not a build) as paid; S (a few days to sp... | Low as paid product (SWOT verdict: don't build); Medium as free lead-funnel a... | Operator-floated 2026-05-22: a vetted online forum for laboratory leaders (directors, managers, supervisors). Pricing as proposed: $5 first year promo, then $5/mo or $50/yr. David McCormick would manage day-to-day moderation with a 50% revenue split. Premise: existing lab-leader communities have decayed (Facebook groups bot- infested, LinkedIn lab-leader groups inactive, listservs dead, ASCP / CLMA discussions gated behind $200+/yr society dues). There is a real gap in the market for an active, vetted, current lab-leader water cooler. |  | Post-COLA. No customer urgency.
38 | Screen-capture video: VeritaCheck method comparison in 60 seconds | Open. Re-parked 2026-05-27 (originally PR #117, abandoned with merge conflicts then closed-and-re-authored at current numbering). Pending operator decision on whether to record this themselves or p... | S for agent prep (storyboard / pre-fill / captions / checklist); ~1 hour of o... | Medium — operator selected this as the highest-impact positioning artifact du... | 30-60 second screen recording demonstrating the "experienced lab tech figures it out in seconds" claim. From blank method-comparison study to completed PDF, no voiceover, no narration, visible cursor motion. Embed autoplay-muted on the marketing site, include in conference follow-up emails. | 2026-05-12 conversation. Michael selected the screen-cap video as the highest-impact positioning artifact, then asked the agent to record it. Agent does not have screen-recording capability; option parked rather than fudged. | Post-COLA, conference-driven.
39 | MediaLab parity hardening (VeritaPolicy approval workflow depth) | Small-item sequence COMPLETE (items 1-5 all shipped; verified against the codebase 2026-09-29, print view PR #1367). Note (2026-10-04): the "delegation" listed here is VeritaPolicy APPROVAL-workflo... | L (1-2 weeks for the high-value items; each independent feature is M) | Medium-High — the C29 build shipped the surface MediaLab markets but depth is... | The VeritaPolicy approval workflow build (C29, 2026-05-29) hit roughly 60-70% MediaLab feature surface. The following gaps remain when comparing against an enterprise MediaLab Document Control deployment: - Quizzes on attestations. Schema columns quiz_score and quiz_total_questions exist on policy_attestations but the quiz authoring + presentation UI was scoped out of Phase 4. MediaLab labs use 5-10 multiple-choice questions per policy to confirm comprehension, not just attestation. Adds compliance defensibility. - PDF watermarking. MediaLab burns user name + timestamp into every downloaded PDF copy as a deterrent against forwarding. We serve clean originals. Add Puppeteer-style overlay at download time. - Per-policy role mapping at department level. MediaLab lets a lab say "only Microbiology Lab Director can approve Microbiology policies." Our required_role is per-step on the workflow, not per-document-by-manual. - Approval delegation. When a reviewer is on vacation, MediaLab supports temporary delegation to a designate. We have no delegation model. - In-browser DOCX editing. MediaLab has a structured editor that creates a Table of Contents from headings. We treat documents as... | 2026-05-29 QA pass after C29 shipped (qa-policy-build.js + qa-policy-ui.js: 54/54 happy path verified). Honest depth assessment surfaced by Michael's "how confident are you" question — see C29 entry for full QA receipts. | Post-COLA. Defensive against MediaLab in head-to-head sales calls.
42 | Outbound demo-invite messaging campaign to 1st-degree LinkedIn contacts | Parked. Plan documented. Implementation deferred until trigger conditions met. Work-pass 2026-10-04: AGENT HALF DELIVERED. Pre-implementation step 5 done: linkedin_search/outbound_messages_v1.md sh... | L (1 week prep + 4-6 weeks of staged sends) | High. Converts existing warm network (~2,500 1st-degree contacts and growing... | A staged outbound DM campaign walking Michael's 1st-degree LinkedIn contacts through tier-segmented demo invitations for VeritaAssure. Goal: convert warmest contacts into demo conversations first, then chain into trials and paid subscriptions. Separate pipeline from COLA cohort follow-up and from content-driven inbound; all three feed the same demo funnel but originate from different warmth sources. | 2026-06-04 session, after weekly LinkedIn invite batch completion (80 sent, cap hit at #84 Victoria Allen).
80 | VeritaPT: the CAP program catalog behind the enrollment picker is incomplete and partly stale (FH9 and RT4 missing, FH2P obsolete) | VERIFICATION STEP 2026-10-07: Lisa supplied the CAP Surveys 2026 and 2027 catalog PDFs; scripts/cap_catalog/extract_cap_catalog.py (pdftotext -layout parse: 756 codes in 2026, 764 in 2027, FH9 and... | S (1-3 days) | High. The enrollment picker is how a lab records its PT coverage for 42 CFR 4... | The "Manage PT Program Enrollments" dialog lists CAP programs from the pt_vendor_programs table (GET /api/veritapt/programs), loaded through the admin vendor-programs endpoint from operator-verified data with provenance in the source column. Production holds 74 CAP programs, source "CAP Surveys catalog (estore.cap.org), compiled 2026-10-06", and only six of them are Hematology: FH2, FH2P, BCP, BP, BMD, ESR. Lisa (2026-10-07): FH9 is missing, RT4 is missing, FH2P is an obsolete event, "I'm sure there are more." The CAP Surveys catalog runs to several hundred programs, so a 74-row compile is a thin first pass, not a catalog. (The API vendor list, 225 programs loaded 2026-10-05, has not been checked the same way.) Fix: rebuild the CAP list from the current CAP Surveys catalog as the source document, code, name, category and analytes per program, verified by a CAP-enrolled director before load (Lisa is the natural verifier; the loader's never-fabricated rule stands); reload with replaceVendor CAP and the catalog edition recorded in source; mark retired programs such as FH2P inactive rather than deleting them so existing enrollments stay valid; then spot-check the API list against i... | Lisa, 2026-10-07 ~10:20 (screenshot, lab 5 VeritaPT enrollments dialog).
81 | Antimicrobial stewardship: the laboratory's share of the hospital program, inside VeritaAssure | Open. Scope document WRITTEN 2026-10-09: docs/ANTIMICROBIAL_STEWARDSHIP_SCOPE.md (verbatim 42 CFR 482.42(b) and 485.640(b); five lab-side parts; MVP M 1-2 weeks; recommends a Stewardship tab in Ver... | M (1-2 weeks) for the lab-side scope; XL if it became a pharmacy-led stewards... | High. Every hospital lab is asked by its stewardship committee for an antibio... | Scope, not build (Lisa, 2026-10-07: "put that in the parking lot"). The likely shape is the laboratory's obligations to the hospital program, not the pharmacy's: an antibiogram builder on CLSI M39 conventions (first isolate per patient per period, the 30-isolate reporting threshold, an annual table with trends), documentation of selective and cascade susceptibility reporting rules, turnaround tracking for rapid diagnostics (Gram stain, blood culture identification), the committee-participation log (lab representation, minutes, actions), and the crosswalk to 482.42, the TJC standard and the CAP microbiology checklist. What already exists to build on: VeritaBench PI carries the blood culture contamination rate; the VeritaPolicy master list already notes antimicrobial stewardship support (antibiogram cadence and reporting cascades) on the microbiology policy; 42 CFR 482.42 is in the requirement library; the microbiology policy template 040 covers isolation and identification. Open questions for the scope doc: which module hosts it (VeritaBench PI, VeritaQA or a new module), isolate data intake (LIS export vs manual), and whether the antibiogram is a PDF deliverable or a live table. | Lisa, 2026-10-07 ~13:40 ("Lets scope an antimicrobial stewardship program in the system"), then parked before scoping.
89 | VeritaCheck page: a discount code shows "applied" and is then dropped | Open. Needs Michael's call on (a) vs (b). | S | Medium. Printed collateral carries codes (LABREADY10, COLA2026); a prospect w... | the "Have a discount code?" box in the free/per-study pricing section of client/src/pages/VeritaCheckPage.tsx validates the code (POST /api/discount/validate) and shows a green "applied" banner, but the only next step is the View Pricing link to /pricing, which neither receives nor reads the code. The code is applied for real only in Account Settings > Discount Code (Activate Subscription). Decide one: (a) carry the code forward (e.g. /pricing?code= and on into Account Settings checkout), or (b) replace the box with a line pointing to Account Settings after sign-in. Found while removing the dead purchase path for #87. | #87 cleanup, 2026-10-08 (read the code; Account Settings is the only page that sends a discount code to checkout).
93 | VeritaMap's SOP review column is separate from VeritaDC | Steps 1 and 2 approved (Michael Q86 = 1, 2026-10-11); build starts Thursday 10/15. Step 3 stays parked. | M (1-2 weeks) | Medium. The map's compliance panel shows "17 SOP overdue" for a lab whose pol... | veritamap_tests.last_sop_review is a hand-entered date per analyte with a 24-month cycle (client/src/pages/VeritaMapMapPage.tsx). VeritaDC tracks each policy's approval, version and next review date. The two never meet, so a lab keeps two sets of review dates or the map reads red. Options: link an analyte's SOP to a VeritaDC document and read its last approval date (the way VeritaCheck studies now stamp cal ver and correlation dates), or drop the SOP column from the map's score. Needs Michael's call. | St. Charles demo dry run, 2026-10-11 (Riverside map 1 reads 82% with "17 SOP overdue").
96 | FAQ promises data retention, exports and a deletion notice the product does not have | Open. Needs Michael's call: correct the copy, or build retention/export/notice to match it. | XS (under a day for the copy fix; the features themselves would be M) | High. Public promises the product does not keep; a buyer's legal or security... | the "Data Retention and Cancellation" answers in client/src/lib/faqContent.ts (lines 605-614 on main, 2026-10-14) say: data is kept 2 years after a subscription ends and can be reactivated; "every module that generates structured data has an Excel or PDF export function"; and after 2 years the account is deleted with an email notice first. In the product, cancelling drops the lab to the free plan, which blocks most exports; Equipment (VeritaMaintain) has no export and VeritaPT has no export button although its page promises a PDF (VeritaPTPage.tsx line 22); no 2-year deletion job or notice email exists. Fix the copy to say what the product does (or build the missing pieces, Michael's call), then check the FAQ page and its prerendered/static copy. | found 2026-10-09 during the Mike Hiltunen and Natalie Lamb replies; promised as "its own item" that day and never raised. Parked 2026-10-14 from the weekly review.
98 | VeritaComp employee form keeps saving an empty TC/TS placeholder row | Open. Waiting on Michael's Q128 (park and build, or leave as is). | XS (under a day, UI change plus a browser test) | Low. No visible effect since the BUG-044 server fix; the data just stays untidy. | ticking TC or TS on the employee form saves an empty specialty placeholder row each time. The BUG-044 server fix makes those rows harmless everywhere they are read. Fix: drop the empty row once a real specialty is added, with a browser test. | BUG-044 follow-up, Q128 (2026-10-12, 9:36 PM ET; Claude recommended parking it until after the 10/14 demo). Q128 was never answered.
100 | Voiding a QC run leaves its auto-created finding open | Built to Claude's recommended option on draft PR #1711 (untouched finding closes with the void reason; a worked finding is flagged "QC run voided"; tests/integration/qc-void-finding.test.ts 11/11 P... | XS to S | Medium. The lab keeps getting reminders for a finding whose run was voided as... | when a QC run that auto-created a finding is voided (e.g., run 957, voided 10/12 as "Entered incorrectly during training"), the finding stays open and its reminders continue. Options: close the finding automatically with the void reason as the closing note, or flag it "run voided, close?" for the supervisor. Michael picks which; either needs an audit-trail entry. | Mike Hiltunen, REQ-063, 2026-10-14. Called "parked" in chat that day but never written here.
101 | "Staff Portal" wording is still on the Plans page and in 11 other screens | Open. | XS to S (copy sweep plus a check of each screen) | Medium. Public pricing names a product that no longer exists; prospects and o... | since 2026-10-09 (#1548, C93) staff sign in to the same VeritaAssure app with a staff login and setup locked; there is no separate Staff Portal. The phrase is still in client code on main (14fa0274): PricingPage.tsx (4, including the "Staff Portal Add-On" heading and the above-250 line), LabMembersPage.tsx (11), VeritaStaffAppPage.tsx (9), StaffPortalPage.tsx (4), VeritaPolicyCompliancePage.tsx (3), App.tsx (2), and one each in InventoryCountWorkflow, HospitalInventoryPage, VeritaCompAppPage, VeritaPolicyMyPoliciesPage, VeritaQCAppPage and VeritaStockPage. Rename to "staff seats" / "staff login" where it describes access, keep the flat-band pricing, and check whether StaffPortalPage is still routed or is dead code. Same sweep for faqContent, seo-metadata, static prerender text and generated PDFs/emails. | Michael 2026-10-14 ("there is no staff portal anymore, correct?") while reviewing the St. Charles reply; Claude had used the term in the draft email and SBAR (both corrected the same evening).
102 | Import MediaLab quizzes into VeritaComp | Waiting on a MediaLab export file from Catherine. | S (1-3 days once a real export file is in hand) | Medium. Labs switching from MediaLab bring years of competency quizzes; retyp... | Catherine Thornton (Redington-Fairview, REQ-074) is rebuilding her MediaLab competency quizzes in VeritaComp™ by hand. Pictures on quiz questions went live 2026-10-14 (#1642, c0dba999), so a converter now has somewhere to put graphs and images. The quiz JSON upload already exists (questions, options, correct answer, explanation, and now an image data URL). What is missing is MediaLab's export format: no sample file exists, so nothing can be built without guessing. The reply to Catherine asked her to send an export if MediaLab offers one. When it arrives, write a converter (script first, in-app upload later if more labs need it). | Catherine Thornton email 2026-10-14 7:27 PM ET; Claude, while building quiz pictures.
105 | Tissue sub-module in VeritaStock: human tissue for implant, tracked from receipt to the patient | Open. Parked, not scoped. The first draft of this entry read "tissue" as anatomic pathology slides and blocks; corrected the same day from the form. | M to L (2-4 weeks) for a tissue sub-module built on VeritaStock's receiving,... | High. Every hospital that stores or implants human tissue (bone grafts and pu... | Michael supplied Heywood Hospital's blood bank tissue form (BB FORM.xlsm) as the core of the module, built as a sub-module of VeritaStock rather than a nineteenth module. The form's workflow, which the sub-module should follow: - Receipt, by Materials Management and then the blood bank (date, time, by): tissue type and supplier picked from a catalog (36 products on the form, for example DBX bone putty from Musculoskeletal Transplant Foundation and Apligraf from Organogenesis), quantity or size, the supplier's ID number, expiration date, transport temperature on receipt with the action taken, and package integrity. - Issue: date and time, issued by the tech and to the courier, delivered to, recipient, requesting physician, with read-back checks (source ID read back, expiration acceptable, integrity acceptable at issue). - Implant: date and time implanted, reconstitution (time, by, solution, solution lot and expiration), implanted by, and the supplier's tissue usage card completed and returned (date). - Other disposition (wasted, returned, expired) with a description and who did it. - A perpetual log of every unit, built from the entries. The federal rule (21 CFR 1271.290, eCFR... | Michael 2026-10-23: "put in parking lot: Tissue storage module with full tracking", then "use this as the core of the tissue module. It can be a sub module within veritastock", with Heywood's BB FORM.xlsm (copy at VLS Leads\Heywood Healthcare\Heywood_BB_Tissue_Form_from_Michael_2026-10-23.xlsm).
106 | Should every account user sign an NDA? Why or why not? | Open. Parked; return to it after the Lifepoint questionnaire is submitted. | N/A to XS. The decision is Michael's (with counsel); if the answer is a click... | Medium. It protects what users see of the product (screens, workflows, regula... | Michael asked whether every person with a VeritaAssure account should sign a non-disclosure agreement, and why or why not. Context from 2026-10-25: Lifepoint's security review is under way with no NDA signed, which limited what Veritas could share (architecture diagram, security policy). Today the published Terms of Service (effective April 23, 2026) only ask users to keep their sign-in credentials confidential; they have no clause protecting Veritas's confidential or proprietary information. Questions to settle when this is picked up: a mutual NDA with each customer organization versus a click-through for every user; what an individual NDA can realistically be enforced against (a lab tech at a customer site) compared with confidentiality terms in the customer agreement and the Terms of Service; whether a click-through adds sign-up friction for staff-portal users; and how this interacts with the Lifepoint agreement's confidentiality section and the IPS. | Michael 2026-10-25: "Parking lot this and return to it later: Should we have all account users sign an NDA? Why or why not?"

## CLOSED
ID | Title | Status | Effort | Importance | Description | Source | Notes
C102 | Calibration Verification + Correlation as one study (was #104) |  | was M / Importance: High. |  | Effort: was M / Importance: High.
C101 | VeritaLab certificate Excel export leaves out the new link and CLIA type (was #103) |  | was XS / Importance: Low. |  | Effort: was XS / Importance: Low.
C100 | VeritaQC finding reminder emails do not name the assay or control level (was #99) |  | was XS / Importance: Medium. |  | Effort: was XS / Importance: Medium.
C99 | The other 76 UTC calendar dates in server/routes.ts (was #97) |  | was S / Importance: Medium. |  | Effort: was S / Importance: Medium.
C98 | VeritaComp: one-click preset reasons when a competency element is marked N/A (was #95) |  | was S / Importance: Medium. |  | Effort: was S / Importance: Medium.
C97 | VeritaLab auto-adds a CLIA certificate keyed on the person, not the lab (was #92) |  | was XS / Importance: Medium. |  | Effort: was XS / Importance: Medium.
C96 | Dead statement in db.ts: a roster "unique index" that can never be created (was #90) |  | was XS / Importance: Low. |  | Effort: was XS / Importance: Low.
C95 | VeritaComp employee page showed the six CLIA elements for a waived instrument (was #91) |  | was S / Importance: High. |  | Effort: was S / Importance: High.
C94 | Surveyor public links list kept expired and revoked links forever (was #94) |  | was XS / Importance: Low. |  | Effort: was XS / Importance: Low.
C93 | Staff logins see the same app as editors, recording allowed, setup locked (was #84) |  | was M / Importance: High. |  | Effort: was M / Importance: High.
C92 | VeritaCheck page: handleBuy defined and never called (was #87) |  | was XS / Importance: Low. |  | Effort: was XS / Importance: Low.
C91 | Plan gates written as blocklists, and an audit that could not see them (was #88) |  | was XS / Importance: Medium. |  | Effort: was XS / Importance: Medium.
C90 | VeritaMap build: "Request we add your instrument" did nothing on step 1 (was #86) |  | was XS / Importance: Medium. |  | Effort: was XS / Importance: Medium.
C89 | VeritaCheck verification: "Remove unit" did nothing (was #85) |  | was XS / Importance: Medium. |  | Effort: was XS / Importance: Medium.
C88 | Env-gated Playwright specs never ran in CI; two shipped unrunnable (was #74) |  | was S / Importance: Medium. The Gate 3 step 8 receipts for signed-in screens... |  | Effort: was S / Importance: Medium. The Gate 3 step 8 receipts for signed-in screens were skipped in CI, so a spec could ship broken and nobody noticed.
C86 | VeritaMap: Manual Diff cell lines never paired with the analyzer differential, so no correlation was triggered (was #76) |  | was S / Importance: High. 42 CFR 493.1281 comparability for the manual vs aut... |  | Effort: was S / Importance: High. 42 CFR 493.1281 comparability for the manual vs automated differential never appeared on the map.
C87 | VeritaMap: remove duplicate demo maps (was #61) |  | was XS / Importance: Low-Medium. |  | Effort: was XS / Importance: Low-Medium.
C85 | An owner who also held a seat on another owner's lab was treated as that seat everywhere (was #82) |  | was S-M / Importance: High. Michael's records were stamped with the St. Charl... |  | Effort: was S-M / Importance: High. Michael's records were stamped with the St. Charles owner's id and his account read that owner's free plan.
C84 | A lab created from the account settings page got no owner membership, so the owner was locked out of it (was #83) |  | was XS / Importance: High. The St. Charles owner (lab 31, evaluation 2026-10-... |  | Effort: was XS / Importance: High. The St. Charles owner (lab 31, evaluation 2026-10-14) had been locked out of her own lab since signup.
C83 | VeritaMap: calibration verification "Not applicable" per test, and the exemption flags honored on the map page (was #77) |  | was S / Importance: High. Lisa's live case on Milford CCL Hematology (45 flag... |  | Effort: was S / Importance: High. Lisa's live case on Milford CCL Hematology (45 flagged tests shown as required, 0 percent score).
C82 | VeritaComp assessment dialog: Element 2 (and 3, 4) date picker nearly unclickable (was #75) |  | was XS / Importance: Medium |  | Effort: was XS / Importance: Medium
C81 | VeritaMap: manual date entry is clunky (was #78) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C80 | In-app Getting Started phase B: live checkmarks on the module how-to cards (was #79) |  | was XS / Importance: Medium |  | Effort: was XS / Importance: Medium
C79 | VeritaQC: Levey-Jennings chart and Westgard rules used two different mean/SD bases (was #65) |  | was S / Importance: High. Live on a paying account (MedStar, Gameday Plymouth... |  | Effort: was S / Importance: High. Live on a paying account (MedStar, Gameday Plymouth): a 1-3s rejection drawn near the chart mean.
C78 | Milford (labs 4/5) house policy format for VeritaDC drafts (was #71) |  | was M / Importance: Medium. Lisa's lab; first renderer-based instance of the... |  | Effort: was M / Importance: Medium. Lisa's lab; first renderer-based instance of the standing house-format courtesy (SCAHC was artifact-based).
C77 | In-app Getting Started, phase A: dashboard card scored from the lab's own tables (was #72) |  | was M / Importance: Medium |  | Effort: was M / Importance: Medium
C76 | VeritaMap "Failed to delete map": half-cascade left shells, VeritaStaff FK blocked the rest (found and fixed 2026-10-07) |  | was S / Importance: High. Michael could not delete four demo maps on lab 3; t... |  | Effort: was S / Importance: High. Michael could not delete four demo maps on lab 3; the same code path would have gutted any map whose instrument was ever assigned to a staff member.
C75 | VeritaMap test-menu accuracy audit: Siemens/Abbott duplicate cleanup (was #57) |  | was M / Importance: High |  | Effort: was M / Importance: High
C74 | VeritaCheck D1 method-comparison verdict: the mean-¦bias¦ override is disputed (was #67) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C73 | VeritaComp legacy program modal shows no VeritaStaff employees (was #59) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C72 | Nightly backup studyCount anomaly on every user-deleted study (was #73) |  | was XS / Importance: Medium |  | Effort: was XS / Importance: Medium
C71 | Nightly backup "integrity ANOMALY" email on every real-user decrease, naming nobody (was #70) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C70 | computeStudyStatus throws at every boot for 4 studies and fail-safes them to FAIL (was #69) |  | was S / Importance: High |  | Effort: was S / Importance: High
C69 | VeritaMap: director attestation, MEC review and unlock stamp EVERY age/sex band of an analyte (was #68) |  | was S / Importance: Medium-High |  | Effort: was S / Importance: Medium-High
C68 | VeritaCheck: Hemoglobin studies render as "Lab-Set Internal Goal", and every narrative cites 42 CFR 493.931 (was #66) |  | was S / Importance: High |  | Effort: was S / Importance: High
C67 | about:blank on PDF opens (window.open token pattern + Adobe Acrobat) (was #63) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C66 | Milford VeritaMap: every value/date save failed, then the AMR autosave loop (was #64) |  | was S + S / Importance: High |  | Effort: was S + S / Importance: High
C65 | Vendor instrument expansion PR #1474, 25 platforms (was #62) |  | was XS / Importance: Medium |  | Effort: was XS / Importance: Medium
C64 | VeritaPT CAP vendor program catalog (was #60) |  | was S / Importance: High |  | Effort: was S / Importance: High
C63 | VeritaCheck instrument-verification multi-select analyte menu (was #58) |  | was S / Importance: High |  | Effort: was S / Importance: High
C62 | Plain-language summary layer: CFR Reference tab (was #30) |  | was M / Importance: Medium |  | Effort: was M / Importance: Medium
C61 | Regenerate the access-inventory Excel with the corrected MD persona (was #44) |  | was XS / Importance: Low |  | Effort: was XS / Importance: Low
C60 | VeritaQC Import Phase A browser click-through (was #40) |  | was XS / Importance: Low |  | Effort: was XS / Importance: Low
C59 | Confirm the finding-closure signer policy (was #43) |  | was XS / Importance: Medium |  | Effort: was XS / Importance: Medium
C58 | VeritaDC per-document attestation tracker + "My Documents" rename (built as #45) |  | was M / Importance: Medium-High |  | Effort: was M / Importance: Medium-High
C57 | Hide sections a lab does not use from a master list (was #47) |  | was S-M / Importance: Medium-High (prospect-requested) |  | Effort: was S-M / Importance: Medium-High (prospect-requested)
C56 | VeritaCEU: curated free continuing-education provider list (was #53) |  | was S / Importance: Low-Medium |  | Effort: was S / Importance: Low-Medium
C55 | VeritaScan: let sites add their own custom questions (was #55) |  | was M / Importance: Medium-High |  | Effort: was M / Importance: Medium-High
C54 | VeritaQC: at-entry warning when a QC point is outside 2 SD (was #56) |  | was S-M (shipped S) / Importance: High |  | Effort: was S-M (shipped S) / Importance: High
C53 | VeritaTrack: quarterly task loaded as monthly until re-saved (was #54) |  | was S / Importance: Medium |  | Effort: was S / Importance: Medium
C52 | VeritaResponse internal NCE / non-conforming event (was #36) |  | was L (shipped as MEDIUM) / Importance: High |  | Effort: was L (shipped as MEDIUM) / Importance: High
C49 | Competency "assessed this cycle" cadence-aware window (was #50) |  | was S-M / Importance: Medium |  | Effort: was S-M / Importance: Medium
C50 | VeritaTrack task owner + owner-only reminder routing (was #51) |  | was S-M / Importance: Medium |  | Effort: was S-M / Importance: Medium
C51 | Designate Medical Director by picking a lab member (was #52, core) |  | was S-M / Importance: Medium-High |  | Effort: was S-M / Importance: Medium-High
C47 | Unregulated-analyte / Alternative Assessment (AAA) coverage (was #18) |  | was S (Phase 3) / Importance: Medium |  | Effort: was S (Phase 3) / Importance: Medium
C48 | VeritaResponse post-survey deficiency module (was #17) |  | was XL / Importance: High |  | Effort: was XL / Importance: High
C45 | Unify coverage/competency recurrence helper (was #49) - closed as non-issue |  |  |  | Closure evidence: Investigated 2026-09-24 before building. The coverage recurrence math (+6-month interval, signed-resets-to-missing, nextDueOn/overdue, isFailVerdict) is ALREADY single-source in server/veritacheckCoverage.ts (computeCoverageFrom). server/coverageReport.ts and the routes.ts coverage export do not recompute it; they consume the computed nextDueOn/overdue/status fields and apply small surface-specific presentation labels (deliberately different vocabularies per surface, so they should not be merged). The only truly identical duplicate is a one-line date formatter. The competency "owed" derivation is NOT the same cadence: competency follows the CLIA milestone schedule (initial / semiannual year 1 / annual, 42 CFR 493.1451(b)(8) and 493.1235), which is a different regulatory interval from the coverage 6-month rule (493.1281 / 493.1255) and must stay separate. No worthwhile extraction; merging the two cadences would be wrong. Closed 2026-09-24. (The year-1 competency-window refinement remains tracked separately as #50.) | 2026-09-24 session, "keep working" pass; scoped read-only, found no real duplication.
C46 | Verified-users product-update send path (wrong-list incident fix) |  |  |  | Closure evidence: Shipped PR #1324 (merged 4e05506a, deploy ACTIVE). New POST /api/admin/users/send targets registered VeritaAssure account holders (the users table), never the Lab Director's Briefing subscriber list. Separate explicitly-named endpoint (not a flag with a dangerous default), account-holder email framing, excludes suppressed emails and RFC-reserved test domains, CC owner, dryRun + testTo previews. Public unsubscribe now upserts a suppression row so opt-outs are honored across both audiences. Live dryRun: 49 verified-user recipients vs 673 on the Briefing list. Receipts: scripts/verify-product-update-send.mts 24/24, tsc clean, rendered sample inspected. Fixes the fallout from the 2026-09-23/24 wrong-list send (a product update went to the 675-person Briefing list). Nothing sends without Michael's explicit "send it." | 2026-09-24 session; Michael selected this as the next build after the #41 close.
C44 | Verify-script convention backfill (was #41) + audit matcher fix |  |  |  | Closure evidence: #41 was fully backfilled on 2026-06-13 (all 8 high-stakes scripts landed; see C30); it had only been mis-filed in OPEN. A 2026-09-24 re-audit initially reported 4 of 5 recent math/logic commits as missing a verify script, which was a FALSE POSITIVE: scripts/audit_verify_script_coverage.py matched only scripts/verify-*.js / .cjs, so it ignored the .mjs / .mts / .ts verify scripts the repo now ships (e.g. verify-ptcoag-multi.mts, verify-tea-criterion-format.mjs). Fixed the matcher to accept .js/.cjs/.mjs/.ts/.mts; re-run shows 5 of 5 covered, 0 debt. The convention is being followed. Closed 2026-09-24. | 2026-09-24 session, "keep working" pass; audit tooling bug found + fixed.
C43 | VeritaStaff instrument-centric (dual) assignment view |  |  |  | Closure evidence: PR #1320. GET/PUT /staff/instruments/:id/employees (transpose of the per-employee endpoints); an "Assign by Instrument" dialog lets a director pick a test system or manual test and check off who runs it. Same staff_employee_instruments join, with the 42 CFR 493.1235(a) duty-change event emitted on newly-added pairs so both orientations trigger the same reassessment. GET verified live on SCAHC lab 2. Closed 2026-09-24. | 2026-09-24 session, Michael ("in staff we should also give the dual view when assigning coverage to test systems or manual tests").
C42 | VeritaComp coverage map (required-vs-assessed matrix, dual view) |  |  |  | Closure evidence: PR #1319 (+ status layer PR #1316). /competency/owed returns per-item assessed (locked passing assessment this cycle on a covering method group) + per-employee CLIA status; CompetencyCoverageMap renders a By-employee / By-instrument matrix (Assessed / Owed / Overdue / Gap). Verified live on SCAHC lab 2 (owed 116, assessed 2, gaps 0). Completes #48 as the VeritaCheck-parity coverage map. Closed 2026-09-24. | 2026-09-24 session, Michael ("are we building the competencies to have a coverage map, same as veritacheck?" then "build it").
C41 | VeritaCheck coverage recurrence (method comparison + cal-ver/linearity + reports) |  |  |  | Closure evidence: PRs #1317 (method comparison), #1318 (cal-ver/linearity), #1321 (report Next-due columns). Periodic verification (correlation/method comparison 42 CFR 493.1281; cal-ver/linearity 42 CFR 493.1255; both 6-month) now recurs: a signed study banks the cycle and rolls to next-due = signed + 6 months instead of reading "done" forever. Status Missing/Failed/Completed-unsigned + a "Next due on" column on-screen and in both coverage exports; also credits the previously-ignored "correlation" study type. Root cause: computeCoverageFrom marked requirements done on mere existence, no date logic. Verified live on SCAHC lab 2 (101 correlations + 11 cal-ver rows now carry a next-due). Engine-level, all facilities. Closed 2026-09-24. | 2026-09-24 session, Michael ("Look at San Carlos... they finished their last set of correlations (all 103) but their menu never reset").
C40 | VeritaComp Competencies Owed derived from VeritaStaff, with gap detection (was #48) |  |  |  | Closure evidence: PR #1314 (squash 2bcb0db9). GET /api/labs/:labId/competency/owed derives each VeritaStaff testing employee's owed competencies from their assigned instruments (staff_employee_instruments -> veritamap_instruments + tests), on the CLIA timeline, and flags instruments not covered by any competency program as gaps. CompetenciesOwedSection renders it on the VeritaComp landing page. Reuses the shipped bridge + suggested-method-groups match rules; no new tables. Verified live on prod with real assignment data: 2 instruments assigned to a demo staffer produced owed=2, gaps=2 (HIGH, Technical Supervisor), then reverted cleanly. Closed 2026-09-24. | 2026-09-23/24 session, Michael ("veritacomp bases what competencies they owe (currently untrue, but needs to be true)"). Option 1 (unify roster on VeritaStaff, match instruments by id).
C39 | VeritaScan line items can attach or link evidence (was #46) |  |  |  | Closure evidence: PR #1312 (squash a1dda93d). VeritaScan scan checklist items now show linked evidence as chips (open link, remove) plus a writer "Link evidence" affordance whose picker links an existing VeritaDC/Library document; a shortcut deep-links to the Library for new (governed) documents. Reuses the already-shipped lab_documents + document_checklist_links + coverage endpoints (URL-pointer only, no file storage, no new tables). Browser-verified live on prod (scan 23): the affordance renders and the picker opens. Closed 2026-09-24. | 2026-09-23 session, Michael. Recurring request. Companion: cross-module evidence display on the VeritaDC policy shipped in PR #1313 (by-target cross-links surfaced in the policy View modal, browser-verified live).
C38 | VeritaTrack calendar month cells expand to reveal hidden tasks (was #45) |  |  |  | Closure evidence: VeritaTrack CalendarView month cells with more than three tasks now expand in place (chevron, "+N more" toggling to "Show less", due dates), so no task is hidden with no path to it (client/src/pages/VeritaTrackAppPage.tsx CalendarView). Shipped 2026-09-23. Closed 2026-09-24. | 2026-09-23 session, Michael screenshot of the VeritaTrack calendar (lab 3, September cell).
C37 | Long Excel column headers no longer clip CFR citations (was #44) |  |  |  | Closure evidence: Verified already fixed on main during the 2026-09-24 session. The VeritaMap export derives the header row height from the longest wrapped header via headerRowHeight(headers, colWidths) (server/routes.ts:15935) instead of a fixed 20, so "Reference Range Attestation (42 CFR 493.1253)" and the other long headers print in full. No new code this session. Closed 2026-09-24. | parked 2026-07-16 (PR 4 Gate 3 render); found already-fixed 2026-09-24.
C36 | License stamp no longer clobbers the §6 header/footer or names the wrong lab (was #43) |  |  |  | Closure evidence: Verified already fixed on main during the 2026-09-24 session. setHeaderFooter (shared/licenseExceljs.ts:155-209) now preserves an existing §6 header and appends (not overwrites) the footer left section, and customer-facing exports name the scoped lab: the VeritaScan library export reads req.scope.lab.name / clia_number (server/routes.ts:16572-16573), not the licensee. No new code this session (avoided regressing the existing fix). Closed 2026-09-24. | parked 2026-07-16 (PR 4 Gate 3 render); found already-fixed 2026-09-24.
C34 | Wire the two static-audit guards into CI (was #43) |  |  |  | Closure evidence: both guards wired into the Multi-Lab Mutations Audit CI workflow (.github/workflows/multilab-mutations-audit.yml) as steps: audit-delete-cascades.mjs (DELETE handlers that orphan non-cascade FK children) and audit-labscoped-write-routes.mjs (client lab-scoped writes with no matching server route). Both exit non-zero on a finding, failing the job. Confirmed 0 findings on main at closure. Closed 2026-06-14. NOTE: a hard merge-block still needs the one-time branch-protection toggle for the "multilab-mutations" check (same caveat as the existing guards already in that workflow).
C35 | Legacy /api/studies over-returns studies across labs (was #44) |  |  |  | Closure evidence: GET /api/studies now scopes its list to the active lab when one is resolved from the Referer (server/routes.ts), so every returned row opens on the lab-scoped detail page; the genuine no-active-lab legacy global fallback is unchanged. drizzle's studies schema lacks lab_id, so the scope filter resolves the lab's study ids via raw SQL (idx_studies_lab_id) and filters on id, mirroring the /api/labs/:labId/studies handler. Closed 2026-06-14.
C30 | Verify-script convention backfill (was #41) |  |  |  | Closure evidence: all 8 high-stakes math/logic commits now ship a paired scripts/verify-*.js (EP17 sensitivity, Deming lot-to-lot, CUMSUM+QC+multi-analyte, EP28 reference interval, Deming/OLS CI, EP15 ANOVA, qualitative method comparison, TEa boundary), per the strike-throughs in #41. Closed 2026-06-13. | scripts/audit_verify_script_coverage.py lookback, 2026-06-02; backfills landed 2026-06-03..06.
C31 | VeritaPT AAA create/update/delete silently no-op in the multi-lab UI |  |  |  | Closure evidence: PR #754 (commit 92ad499) added lab-scoped POST/PUT/DELETE /api/labs/:labId/pt/aa-records. The UI posted to the lab-scoped path but only GET existed, so writes fell through to the SPA catch-all (200 + index.html, nothing written); the UI did not check the response, so "Add AAA Record" cleared the form and looked saved. Confirmed in-browser (rows 20 -> 20), fixed, and prod-verified (create adds a row, delete removes it). Also fixed the lab-tagging defect (legacy route mis-filed records to the user's default lab on multi-lab accounts). | 2026-06-13, found during #18 Phase 3 QA; scripts/audit-labscoped-write-routes.mjs now guards the class.
C32 | VeritaComp "Unlock assessment" false-success no-op |  |  |  | Closure evidence: PR #755 (commit 4234007) moved the unlock route to /api/labs/:labId/competency/assessments/:id/unlock (the path the client calls). It had been registered at the non-:labId path while using labScopeMiddleware (which 400s without :labId), so the client's lab-scoped POST hit the SPA fallback (200), and the client's if (!res.ok) showed a false "Assessment unlocked" toast while the signed assessment stayed locked. Prod-verified (path now returns JSON 404, not SPA HTML). | 2026-06-13, found by scripts/audit-labscoped-write-routes.mjs.
C33 | FK-cascade delete 500s + NavBar laptop-width overflow |  |  |  | Closure evidence: PRs #749/#750 fixed NavBar horizontal overflow at laptop widths (collapse to the hamburger below 1560px); prod-verified at 1280-1920 with the longest lab name. PRs #751/#752 fixed 6 delete handlers that 500'd on foreign-key constraints (VeritaCheck verification analytes; VeritaResponse finding effectiveness checks, in BOTH the lab-scoped and legacy handlers; VeritaMap instrument staff links; competency assessment element docs; competency quiz assignments). All prod-verified 500 -> 200. scripts/audit-delete-cascades.mjs guards the class. | 2026-06-13 browser QA of the A7-D4 wave + retro-QC of the 72h PR window.
C1 | FAQ "over 25 years" -> "over 23 years" |  |  |  | Closure evidence: client/src/pages/FAQPage.tsx line 20 reads "over 23 years" as of 2026-05-01. | session 299e9a73 turn 14, ~2026-04-28.
C5 | David's VeritaQA grey-button bug (seat permissions mode) |  |  |  | Closure evidence: PR #10 squash-merged as commit a43fbba on 2026-05-01 23:19 MST. Railway deploy succeeded; deployed bundle (/assets/index-CBVwW2mk.js) confirmed to contain new strings ('VeritaQA™ Suite', 'VeritaStock™', 'edit_all', 'view_all', 'Inherits future modules'). Resolver in shared/schema.ts (resolveSeatPermission) auto-upgrades David's stored permissions (9-of-9 keys = edit, veritabench/veritastock absent) to effective edit on the new modules without any DB write. Verified locally against his exact stored shape (14 of 14 expected outcomes matched). | 2026-05-01 David's report; veritabench + veritastock weren't in MODULE_LIST so seat permissions silently defaulted to view, greying the browse button on /veritabench/pi line 323.
C2 | TeamPage present-tense "TJC surveyor" check |  |  |  | Closure evidence: site-wide search confirmed all surveyor language is past-tense, consistent with user's 2021-2025 service. User closed the item in session 299e9a73 turn 4. | session 299e9a73, ~2026-04-28.
C3 | My Studies CSV/XLSX export (John as design partner) |  |  |  | Closure evidence: client/src/pages/DashboardPage.tsx line 46 calls /api/my-studies/export. server/routes.ts line 1491 implements the endpoint. Pulled forward into pre-COLA per user instruction. | session 299e9a73 turn 5, ~2026-04-28.
C4 | Rotate GitHub PAT (because old PAT was committed in SESSION_HANDOFF files) |  |  |  | Closure evidence: no ghp_* or github_pat_* patterns in current SESSION_HANDOFF.md or SESSION_HANDOFF-2.md as of 2026-05-01. | session 299e9a73, ~2026-04-28.
C6 | VeritaPolicy service-line filtering removed (formerly #4) |  |  |  | Closure rationale (operator decision 2026-05-10): Keep all VeritaPolicy rows. CFR-only references with no accreditor reference are intentional. Labs are welcome to N/A specific lines that do not apply to them. The "service-line filtering" reframing of the original report misread the design intent. | Operator instruction 2026-05-10 in this session.
C7 | CLIA number format validation (formerly #13) |  |  |  | Closure evidence: shared/validateClia.ts defines CLIA_REGEX = /^\d{2}D\d{7}$/ (line 24), validateClia() helper with whitespace and dash stripping plus uppercasing (lines 43-57), and CLIA_FORMAT_HINT user-facing error message (lines 26-27). Used in client/src/pages/AccountSettingsPage.tsx:393 as placeholder text. The centralized helper described in the original parking lot fix shape exists and behaves as specified. | Agent verification 2026-05-10 via grep + file read. Operator confirmed shipped 2026-05-10.
C8 | VeritaMap lab-wide menu toggle (formerly #19) |  |  |  | Closure evidence: client/src/pages/VeritaMapLabwidePage.tsx exists and implements the labwide read-only union view. Route is registered in client/src/App.tsx. Toggle integration appears in client/src/pages/VeritaMapAppPage.tsx and client/src/pages/VeritaMapMapPage.tsx. Phase 1 of the original parking lot plan (read-only union view, per-session toggle) shipped. | Agent verification 2026-05-10 via grep + file read. Operator confirmed shipped 2026-05-10.
C9 | Tier-1 smoke test checklist (formerly #6) |  |  |  | Closure evidence: docs/smoke-test-tier1.md documents the Tier-1 smoke-test process and post-deploy verification steps. Shipped via PR #81 as part of the 2026-05-10 wave. | Operator instruction 2026-05-10 in this session.
C10 | Per-module gating (formerly #7) |  |  |  | Closure evidence: Client-side useIsReadOnly module keys wired on client/src/pages/VeritaPolicyAppPage.tsx and client/src/pages/VeritaLabAppPage.tsx. Server-side requireModuleEdit('veritapolicy') and requireModuleEdit('veritalab') guards added on /api/veritapolicy/* and /api/veritalab/* write routes in server/routes.ts; requireModuleEdit('veritatrack') added on 7 write routes in server/veritatrack.ts. Verified by operator: seat user set to View on veritapolicy blocks UI saves and returns 403 from curl; restoring Edit resumes writes; same pattern verified for veritalab and veritatrack. Shipped via PR #76. | Operator instruction 2026-05-10 in this session.
C11 | VeritaStock shipped copy (formerly #8) |  |  |  | Closure evidence: client/src/pages/ArticleInventoryManagementPage.tsx line 305 footer reads "platform that includes VeritaStock™" instead of the prior "planned for a future release" wording. Verified live on /resources/laboratory-inventory-management. Shipped via PR #75. | Operator instruction 2026-05-10 in this session.
C12 | Admin report one-row-per-lab (formerly #14) |  |  |  | Closure evidence: /api/admin/report rewritten in server/routes.ts (~line 595) to LEFT JOIN labs on owner_user_id, expanding multi-lab owners into one row per lab with the lab's own CLIA. Backward-compatible response shape returns both labs (new) and users (legacy alias) so the rollout is revertible. client/src/pages/AdminReportPage.tsx updated to read data.labs ?? data.users, use effective_clia_number / effective_lab_name, and key React rows by lab_id when present. Operator-confirmed multi-lab owners now require a second labs row added via Account Settings to surface two rows (data prerequisite, not a code bug). Shipped via PR #85. | Operator instruction 2026-05-10 in this session.
C14 | UI relabel "CLIA TEa" -> "Lab-Set Internal Goal" (formerly #1) |  |  |  | Closure evidence: Shipped across four PRs over 2026-05-10. | Operator instruction 2026-05-10 in this session.
C13 | WSLH PT vendor (formerly #15) |  |  |  | Closure evidence: Shipped 2026-05-10 via PR #79 (merge commit eeebc6e; merged after rebase to resolve a server/db.ts collision with PR #80's aa_records migration block, with both blocks preserved side by side). pt_enrollments_v2 CHECK constraint rebuilt in server/db.ts to include 'WSLH' via idempotent CREATE NEW + INSERT SELECT + DROP + RENAME migration block. shared/wslhCatalog.ts added with 6 starter programs (1310 General Chem, 1260 Cardiac, 1080 Blood Lead, 1524 HbA1c, 4190 Hepatitis Serology, 2230 Hematology). 'wslh' added to VALID_PT_VENDORS in server/routes.ts. WSLH wired into the vendor selector on client/src/pages/AccountSettingsPage.tsx and into the vendor list on client/src/pages/VeritaPTAppPage.tsx. Migration log line [migration] pt_enrollments_v2 vendor CHECK rebuilt to include 'WSLH' is the post-deploy success signal. Shipped via PR #79. | Operator instruction 2026-05-10 in this session.
C15 | VeritaStock lot tracking + expiration + reorder alerts (formerly #21) |  |  |  | Closure evidence: VeritaStock™ shipped the bench-level inventory features the Perplexity competitor analysis identified as a gap: | Originally Perplexity competitor analysis 2026-05-10. Audit 2026-05-21 confirmed the feature set ships today.
C16 | PAL studies guided workflow (formerly #23) |  |  |  | Closure evidence: VeritaCheck™ already ships the Precision / Accuracy / Linearity (PAL) study set under EP-protocol naming: | Originally Perplexity competitor analysis 2026-05-10. Audit 2026-05-21 confirmed the EP studies cover the PAL framing in full.
C17 | Source-grounded 21/29/45 CFR + 42 CFR 482-485 (formerly #26) |  |  |  | Closure evidence: PR #301 (commit 8c27806, merged 2026-05-21) source-grounded the 74 remaining non-493 entries in server/cfrRequirements.ts against verbatim eCFR XML. Breakdown shipped: | PR #301; tasks #18 in the in-session task tracker.
C18 | VeritaPolicy "Non CLIA" chapter rename (formerly #3) |  |  |  | Closure evidence: PR #300 (commit 34d7707, merged 2026-05-21) renamed all 44 user-facing chapter labels in server/cfrRequirements.ts that started with "Non CLIA". The string was an artifact of the generator script categorizing CFR rows by whether they sat inside or outside 42 CFR Part 493 (CLIA), and the internal taxonomy was leaking onto the user-facing /veritapolicy page. | CAP customer screenshot of the /veritapolicy chapter headers, 2026-05-01 evening. PR #300; tasks #17 in the in-session task tracker.
C19 | VeritaStock department-scope toggle (formerly #31) |  |  |  | Closure evidence: PR #319 (commit d01f5fe, merged 2026-05-22) shipped the persistent dept-scope toggle on VeritaStockPage. A new "Working in:" selector in the page header lets a user choose between "Lab-wide" (default) or any specific department. The choice is persisted to ui_preferences.veritastock_scope and restored on every reload so users who manage a single department land in their own workspace without re-filtering. | John, San Carlos lab, 2026-05-21. Same conversation that drove the vendor dropdown (PR #304), FILTERED VIEW banner (PR #305), and Snap Order workflow (PR #307).
C20 | Primary-lab seat counting (formerly #12) |  |  |  | Closure evidence: is_primary_lab INTEGER NOT NULL DEFAULT 0 column was added to the lab_members table at db.ts:1276, with the ALTER TABLE migration at db.ts:1302 ensuring the column is added on production databases that pre-date the change. The first-lab-created default is wired at db.ts:1387 (initial INSERT sets is_primary_lab=1 for the seed owner) and db.ts:1446 (membership lookups prefer is_primary_lab=1 ordering). | 2026-05-07 multi-lab discussion. Build shipped as part of the Multi-Lab Tier 2 architecture work (Phase 3.x series, prior sessions). Status drift discovered 2026-05-22 during parking-lot audit.
C21 | Multi-lab pricing model — Option A (formerly #11) |  |  |  | Closure evidence: PR #322 (commit 0ccd925, merged 2026-05-22) added the customer-facing line to the pricing page that reflects the parking-lot decision. Initial copy overspecified by asserting "each lab gets its own subscription at its own tier" -- that language committed the public page to a pricing structure that contradicts Enterprise+ positioning ("custom pricing, custom scope"). Softened the same session in a follow-up PR. Final block on client/src/pages/PricingPage.tsx, immediately after the Enterprise+ block, reads: | 2026-05-07 multi-lab discussion (Lisa Veri's canonical-case session). PR #322 (initial build); softening PR follow-up the same day after the operator caught the Enterprise+ conflict.
C22 | VeritaOps cost-per-test module (formerly #10) |  |  |  | Closure evidence: v1 of the VeritaOps Cost-Per-Reportable-Test (CPRT) module shipped across PR #325 through PR #330 on 2026-05-22. The module is feature-complete for the typical lab director workflow. | This thread, 2026-05-07 12:05 PM CDT, user message: "Parking lot: build an operations module for cost per test calculations." Scoping pass + research session 2026-05-22; v1 build same session. PRs #325 through this one.
C23 | CCL lab name visual disambiguation in lab switcher (formerly #34) |  | XS (under 1 day, actual) | Low — cosmetic; only mattered when Lisa or Michael picked the wrong lab from... | Effort: XS (under 1 day, actual) Importance: Low — cosmetic; only mattered when Lisa or Michael picked the wrong lab from the dropdown. | flagged 2026-05-23 immediately after provisioning Lisa's CCL lab; closed 2026-05-24.
C24 | VC Unlimited Y1/Y2 price disclosure UX (formerly #35) |  | XS (under 1 day, actual) | Low when shipped (proactive, no customer complaint yet) — but high if a procu... | Effort: XS (under 1 day, actual) Importance: Low when shipped (proactive, no customer complaint yet) — but high if a procurement reviewer later disputes the $499 renewal as undisclosed. | Pricing rebuild 2026-05-23; closed 2026-05-24 proactively before any customer dispute.
C25 | VeritaQC Phase 1 (Levey-Jennings + Westgard live engine) (formerly #20) |  | L (about 5 days end-to-end, actual: Phase 0 schema → Phase 1A evaluator → 1B... | High — largest single gap vs myLabCompliance.io per Perplexity competitor ana... | Effort: L (about 5 days end-to-end, actual: Phase 0 schema → Phase 1A evaluator → 1B entry UI → 1C daily review → 1D monthly PDF + attestation) Importance: High — largest single gap vs myLabCompliance.io per Perplexity competitor analysis; promotes VeritaAssure from documentation tool to lab operations platform. | Perplexity competitor analysis 2026-05-10. Scoping confirmed via the build_phase1_mockup.py iterations 2026-05-24. Shipped 2026-05-25.
C26 | VeritaLab CMS-116 application support + state licensing registry (formerly #22) |  | M (1-2 weeks for v1, actual) | Medium — competitor parity (myLabCompliance.io) plus useful at lab startup an... | Effort: M (1-2 weeks for v1, actual) Importance: Medium — competitor parity (myLabCompliance.io) plus useful at lab startup and at certificate-type changes. | Perplexity competitor analysis (myLabCompliance.io), 2026-05-10. Reclassified as a VeritaLab extension 2026-05-25. Shipped 2026-05-28.
C27 | Active vs view-only seat split (formerly #33) |  | M (~1 week of engineering, actual: shipped in a single multi-PR session) | Medium — closed the gap between /pricing copy and product behavior; gives sal... | Effort: M (~1 week of engineering, actual: shipped in a single multi-PR session) Importance: Medium — closed the gap between /pricing copy and product behavior; gives sales a clean answer for "do you charge for our medical director?" | Pricing analysis doc Decision 3 (2026-05-21); MEDIUM scenario revised 2026-05-29 to retire the "unlimited view-only" claim. Shipped 2026-05-28.
C28 | "Why VeritaCheck" comparative one-pager (formerly #37) |  | S (one design pass + four claim paragraphs + PDF + matching marketing-site pa... | Medium — closed a positioning gap surfaced by six COLA conference attendees a... | Effort: S (one design pass + four claim paragraphs + PDF + matching marketing-site page, actual) Importance: Medium — closed a positioning gap surfaced by six COLA conference attendees attached to a legacy verification tool; converts product-quality advantage into a leave-behind Lisa can hand out. | 2026-05-11 / 2026-05-12 conference notes review with Michael. Conference attendees (Whitehead, Odegard, Othman, Molinelli, Kyle, Allred) expressed interest in equivalent / superior product. Shipped 2026-05-28.
C29 | VeritaPolicy approval workflow — MediaLab functional mirror |  | XL (one focused session, 12 PRs landed) | High — replaces MediaLab Document Control ($752/$2,250 starting price, scalin... | Effort: XL (one focused session, 12 PRs landed) Importance: High — replaces MediaLab Document Control ($752/$2,250 starting price, scaling to $10K-$20K/yr at enterprise per Capterra public data) with an included VeritaPolicy feature; closes a real positioning gap and gives sales a direct comparator line. | Pricing strategy conversation 2026-05-29 (Michael: "I don't like bolt-ons; we should replicate this") → scoped 8 phases → shipped all 12 PRs in single session. Shipped 2026-05-29.

## RETIRED
ID | Title | Status | Effort | Importance | Description | Source | Notes
R4 | Mini-LIS module (formerly #24) — HIPAA boundary |  |  |  | Rejected 2026-05-21 by operator decision. | 2026-05-21 strategic decision (this session).
R5 | Phlebotomy module (formerly #25) — HIPAA boundary |  |  |  | Rejected 2026-05-21 by operator decision, same basis as R4. | 2026-05-21 strategic decision (this session).
R6 | WSLH PT booth follow-up email (formerly #16) — stale |  |  |  | Closed 2026-05-21 by operator decision. | 2026-05-21 cleanup decision (this session).
R1 | Rotate Railway token because it appeared in chat |  |  |  | Reason: Per session 299e9a73 turn 7 (and STANDING_REQUIREMENTS.md "CREDENTIAL HANDLING" section): tokens the user pastes in our chat are not a leak; the agent does not auto-park rotation. The original "rotate GitHub PAT" item was added because the PAT had been written into committed SESSION_HANDOFF.md files in past sessions and pushed to the repo, which is an actual leak. Token-in-our-conversation is not. | session 299e9a73 turn 7, ~2026-04-28.
R2 | Real Stripe checkout abandonment diagnostic (formerly #2) |  |  |  | Reason: Operator decision 2026-05-10 — abandoned. Not pursuing a Stripe-session-based abandonment diagnostic. The original concern (text-parsed inference incorrectly presented as diagnosis) is noted as a class of error to avoid; the build itself is no longer wanted. | Operator instruction 2026-05-10 in this session.
R3 | VeritaScan sign-off date field (formerly #9) |  |  |  | Reason: Operator clarification 2026-05-10 — VeritaScan sign-off is not a regulatory requirement. The cross-reference value with VeritaMap correlation (originally proposed as the motivating use case) does not justify adding the schema and UI. No code change. | Operator instruction 2026-05-10 in this session.